## Slide 1: Test Estimation
Test Design & Strategy · Unit 9
Answering "how long will testing take?" with something better than a guess
30 minutes
Notes: You have now seen the whole testing workflow: choosing types and a strategy, analysing requirements, designing scenarios and test cases, and managing defects. Every one of those activities takes time. Sooner or later your lead will ask how long testing will take. This chapter teaches you to answer with a reasoned estimate instead of a guess.

## Slide 2: What this unit covers:
LEARNING OBJECTIVES
1
Explain why testing needs estimation.
2
List the factors that contribute to testing effort.
3
Apply five approaches: expert judgement, WBS, test-case-based, three-point and historical.
4
Calculate a three-point estimate with E = (O + 4M + P) / 6.
5
State your assumptions and convert effort into a schedule.
Notes: Five objectives. The formula in objective four is the one thing worth memorising; everything else is about thinking through the work completely and being honest about what your number depends on.

## Slide 3: Five jobs an estimate does
WHY ESTIMATE?
Planning: the project manager needs dates for the release plan.
Resourcing: how many testers, devices and environments?
Negotiation: if time is fixed, what scope can we test, and which risks stay untested?
Credibility: testing gets squeezed at the end; a reasoned estimate protects quality.
Tracking: estimate vs. actual makes the next estimate better.
An estimate is not a promise. It is a best prediction based on stated assumptions. When an assumption changes, the estimate changes too.
Notes: Testing is the phase most often squeezed when development runs late. If you can show where the hours come from, you can negotiate scope instead of silently cutting corners. And remember the callout: an estimate is a prediction with assumptions, not a commitment carved in stone.

## Slide 4: The work itself
WHAT DRIVES EFFORT · 1 OF 2
Factor | How it affects effort | Example
Scope | More features and modules, more testing | Login only vs. full checkout
Complexity | Logic, integrations and rules need more scenarios | 3 payment gateways vs. a static page
Requirements | Each requirement and AC needs coverage | 12 stories × ~6 AC each
Test cases | Design, review and execution scale with count | 40 vs. 400 test cases
Test data | Accounts, products, cards, coupons, masked data | 20 users in different states
Environments | Builds, configs, devices, browsers, sandboxes | Payment gateway sandbox access
Notes: These six factors describe the size and shape of what you must test. Beginners usually count only test cases, but test data and environment setup are real hours too, and they are often the tasks that slip.

## Slide 5: The work around the work
WHAT DRIVES EFFORT · 2 OF 2
Factor | How it affects effort | Example
Automation | Building, debugging, maintaining scripts | ~1–3 h per automated test at first
Regression | Re-running existing tests every cycle | 2 cycles × 1 day
Defect retesting | Logging, reproducing, retesting, re-running | Often 15–30% of execution
Team capacity | Testers, skill, availability, leave, meetings | 2 testers × 6 productive h/day
Risk | Unclear requirements, new tech, unstable builds | Add contingency (a buffer)
Productive hours are not working hours. In an 8-hour day a tester has about 6 productive testing hours after meetings, stand-ups, email and environment issues.
Notes: These are the hours beginners forget. Defect work alone is often fifteen to thirty percent of execution effort. And the six-hour productive day is the single most useful number in this chapter: plan with eight and you are late from day one.

## Slide 6: Ask the people who've done it before
APPROACH 1 OF 5 · EXPERT JUDGEMENT
The QA lead, senior testers and developers estimate from experience.
Wideband Delphi
Experts estimate independently, discuss the differences, then re-estimate.
Planning Poker
Agile teams estimate stories together, in story points.
Pro: fast; uses real-world knowledge
Con: subjective; depends on the expert
Notes: We go from the simplest approach to the most data-driven. Expert judgement is what most teams do first. Delphi and Planning Poker both reduce one person's bias by getting independent estimates before discussion: the conversation about why two people disagree is often where forgotten work appears.

## Slide 7: Break it down, estimate each piece, add up
APPROACH 2 OF 5 · WORK BREAKDOWN STRUCTURE
Test Login Module
1. Planning & requirement analysis
3 h
2. Test design
2.1 Write scenarios
2 h
2.2 Write test cases
10 h
2.3 Review test cases
2 h
3. Test data & environment setup
4 h
4. Test execution (cycle 1)
8 h
5. Defect reporting & retesting
4 h
6. Regression (cycle 2)
4 h
7. Test summary report
2 h
TOTAL
≈ 39 h
Pro
Thorough. Reveals forgotten tasks like test data and reporting.
Con
Takes time, and needs a clear scope.
Small tasks are easier to estimate accurately than one big one.
Notes: A work breakdown structure for testing the login module. Notice that execution is only eight of the thirty-nine hours. The items in orange, test data and the summary report, are the ones people forget when they estimate in one go.

## Slide 8: Count, classify, multiply
APPROACH 3 OF 5 · TEST-CASE-BASED
Complexity | Count | Design / TC | Execution / TC | Total
Simple | 20 | 10 min | 5 min | 20 × 15 min = 5.0 h
Medium | 15 | 20 min | 10 min | 15 × 30 min = 7.5 h
Complex | 5 | 40 min | 20 min | 5 × 60 min = 5.0 h
Total | 40 |  |  | 17.5 h (design + 1 run)
Then add the overheads: setup, defects, regression, reporting.
Pro: objective, easy to explain
Con: needs a test-case count up front
Notes: If you don't have test cases yet, a rough rule is the number of scenarios from chapter six times about two. The 17.5 hours covers design plus one execution cycle only. Setup, defect handling, regression and reporting all come on top.

## Slide 9: Build the uncertainty into the number
APPROACH 4 OF 5 · THREE-POINT (PERT)
O
Optimistic
Everything goes well
M
Most likely
Realistic
P
Pessimistic
Unstable builds, many defects
E = (O + 4M + P) / 6
SD = (P − O) / 6
Notes: Three-point estimation admits that we don't know exactly. Estimate three values for each task or for the total. The PERT formula is a weighted average: the most likely value counts four times. The standard deviation, optional, tells you how wide the uncertainty is. Its weakness: garbage in, garbage out. O, M and P are still judgement.

## Slide 10: O = 20 h, M = 30 h, P = 52 h
WORKED EXAMPLE · CHECKOUT TEST EXECUTION
E
(20 + 4×30 + 52) / 6 = 192 / 6 = 32 h
SD
(52 − 20) / 6 = 32 / 6 ≈ 5.3 h
E ± SD
32 − 5.3 ≈ 27 h to 32 + 5.3 ≈ 37 h
HOW TO SAY IT
"About 32 hours, likely between 27 and 37."
Notes: Walk through the arithmetic slowly. Four times thirty is one hundred and twenty; add twenty and fifty-two to get one hundred and ninety-two; divide by six to get thirty-two. Notice E is a little higher than M, because the pessimistic tail is longer than the optimistic one. Giving a range is more honest than a single number, and it is easy to justify.

## Slide 11: Let past projects tell you
APPROACH 5 OF 5 · HISTORICAL
Last 3 releases: the team averaged 0.9 h of total testing effort per test case (design, execution, defects and regression).
60 × 0.9
new feature, ~60 test cases
54 h
baseline from history
≈ 62 h
+15% for a new payment gateway
Pro: grounded in reality
Con: needs good records and comparable projects
Notes: Historical estimation is only as good as your records, which is one more reason to track estimate versus actual. Always adjust for what is different this time: here a new payment gateway adds fifteen percent, so fifty-four times one point one five is about sixty-two hours.

## Slide 12: Each has a sweet spot and a trap
COMPARING THE APPROACHES
Approach | Best when | Main risk
Expert judgement | Early, quick, little data | Bias, optimism
WBS | Scope is clear | Forgetting tasks
Test-case-based | Scenarios or test cases are known | Wrong test-case count
Three-point | Uncertainty is high | Garbage in, garbage out
Historical | Similar past projects with data | Projects not comparable
In practice, combine them: build a WBS, estimate each task with three-point, then sanity-check against history and expert opinion.
Notes: No single approach is best. The combination at the bottom is what experienced QA leads actually do: the WBS stops you forgetting work, three-point handles uncertainty, and history and experts catch numbers that look wrong.

## Slide 13: Person-hours are not calendar days
FROM EFFORT TO SCHEDULE
Duration (days) = Effort (h) ÷ (Testers × Productive h per day)
60 h ÷ (2 × 6 h/day) = 60 ÷ 12 = 5 working days
WATCH OUT FOR
Waiting for builds and fixes (can't be parallelised)
Holidays and leave
Dependencies on other teams
Notes: Effort is how much work; duration is how long on the calendar. Divide effort by daily team capacity, using productive hours, not eight. Then remember that adding testers doesn't help while everyone waits for a build or a fix.

## Slide 14: An estimate without assumptions can't be defended
ALWAYS STATE YOUR ASSUMPTIONS
Requirements are stable; changes are re-estimated
Environment available and stable from Day 1
Builds pass the smoke test
Critical and High defects fixed within 1 day
Test data provided by dev or created by QA
2 testers, 6 productive h/day, no planned leave
Payment sandbox access available
Also list what is out of scope, e.g. "Performance and security penetration testing are not included."
Notes: Each assumption is a condition your number depends on. When the environment arrives three days late, you can point to the assumption and re-estimate, instead of being blamed for a missed date. The out-of-scope list does the same job for work nobody asked you to plan.

## Slide 15: Five ways an estimate goes wrong
COMMON BEGINNER MISTAKES
Estimating only execution time. Forgetting design, data, setup, defects, regression, reporting.
Assuming 8 productive hours a day.
No contingency for unstable builds or a high defect count.
One number, no assumptions.
Never comparing estimate vs. actual, so estimates never improve.
Notes: Every one of these produces a number that is too low or can't be defended. The first is by far the most common: in the WBS example, execution was eight hours out of thirty-nine.

## Slide 16: Estimate testing for a login module
PRACTICE · 9 MINUTES
20
functional scenarios
40
test cases
5
browsers
2
testers
Yes
regression required
Some
automation required
Calculate the effort, convert it to a schedule, and list your assumptions.
Notes: Nine minutes. Work in pairs if you like. Start with a WBS so you don't forget tasks, use test-case counts where you can, and write down every assumption you make, especially about the five browsers and the automation. There is no single correct number.

## Slide 17: Start with the assumptions
MODEL ANSWER · 1 OF 3
1
Design 15 min per TC; execution 12 min per TC on the primary browser (Chrome).
2
A cross-browser subset of 15 UI-relevant TCs runs on the other 4 browsers at ~8 min each.
3
10 TCs (smoke + core regression) automated at ~1.5 h each.
4
Defect logging and retesting ≈ 25% of execution.
5
2 regression cycles of ~4 h manual each; automated runs are unattended.
6
Management, meetings and reporting ≈ 10% overhead.
7
2 testers, 6 productive h/day each; the environment is stable.
Notes: Assumption two is the important judgement call: not all forty test cases need to run on all five browsers. Only the UI-relevant ones do, and repeat runs are faster. Writing it down means the stakeholder can challenge it, and we'll see on the last answer slide what it costs if they do.

## Slide 18: WBS plus test-case counts
MODEL ANSWER · 2 OF 3
Task | Calculation | Hours
Requirement analysis & scenario review |  | 2
Test case design | 40 × 15 min | 10
Test case review |  | 2
Test data & environment (5 browsers) |  | 4
Execution: primary browser | 40 × 12 min | 8
Execution: 4 other browsers | 15 × 4 × 8 min | 8
Defect logging & retesting | 25% × (8 + 8) | 4
Automation (10 TCs) | 10 × 1.5 h | 15
Regression | 2 cycles × 4 h | 8
Subtotal |  | 61
Management & reporting | 10% × 61 ≈ 6.1 | 6
Most likely total (M) |  | ≈ 67
Notes: Each line traces back to an assumption on the previous slide. Notice automation at fifteen hours is the single biggest item, larger than all execution combined. The sixty-seven hours becomes our most likely value, M, for a three-point estimate.

## Slide 19: Three-point, schedule, and how to say it
MODEL ANSWER · 3 OF 3
O = 55 h (few defects, stable builds)
M = 67 h
P = 95 h (unstable builds, flaky automation)
E = (55 + 268 + 95) / 6 = 418 / 6 ≈ 70 h
SD = (95 − 55) / 6 ≈ 6.7 h
Capacity = 2 × 6 = 12 h/day
70 ÷ 12 ≈ 5.8
6 working days
"About 70 person-hours, ~6 working days with 2 testers, likely between 63 and 76 hours. Assumes a stable environment, 15 cross-browser TCs, 10 automated tests and 2 regression cycles. If all 40 tests must run on all 5 browsers, add ~13 hours."
Where ~13 h comes from: 40 × 4 × 8 min = 1,280 min ≈ 21.3 h, minus the 8 h already planned ≈ 13.3 h. Show the impact of changing an assumption.
Notes: Four times sixty-seven is two hundred and sixty-eight. The range sixty-three to seventy-six is E plus or minus one standard deviation. The last sentence of the quote is what makes this a professional estimate: it tells the stakeholder exactly what happens if they challenge assumption two. Your numbers will differ, and that's fine. Estimates are judged on completeness of tasks, clear assumptions and sound arithmetic, not on matching a correct number.

## Slide 20: Five questions
QUICK CHECK
1
Write the three-point (PERT) formula.
2
O = 10, M = 16, P = 28. What is E?
3
Name four factors that contribute to testing effort besides executing test cases.
4
48 hours of effort, 2 testers, 6 productive h/day. How many days?
5
Why must an estimate include assumptions?
Notes: Answers: 1. E equals O plus four M plus P, all divided by six. 2. Ten plus sixty-four plus twenty-eight is one hundred and two; divided by six is 17 hours. 3. Any four of: test design, test data preparation, environment setup, automation, regression, defect retesting, reporting, meetings, risk and uncertainty. 4. 48 divided by 12 is 4 days. 5. So stakeholders know what the number depends on, and the estimate can be revised when an assumption changes.

## Slide 21: A prediction, with its assumptions
KEY TAKEAWAYS
Estimation supports planning, resourcing and negotiation. It is not a promise.
Effort comes from scope, complexity, test cases, data, environments, automation, regression, defects, capacity and risk.
WBS so nothing is forgotten, test-case-based for objectivity, three-point for uncertainty, history for realism.
E = (O + 4M + P) / 6
Effort ÷ (testers × productive hours) = duration. Always state your assumptions.
Next: Unit 10, Capstone: putting everything together on an e-commerce checkout.
Notes: Recap. You can now explain where testing hours come from, estimate them five ways, and turn them into a schedule you can defend. In the capstone you'll put everything from the course together on one realistic feature.